RestoBooks

Agentic Finance Platform for Restaurants

Strategic Build Plan: From InvoiceManagementStore to Full POC

| ✅ Built Invoice AI + Lambda API | 🔨 Building Bank Feed + Categorization | 🎯 Target Toast + Full Agent Loop |
| --- | --- | --- |

# 1. Where You Stand: What You've Already Built

Your InvoiceManagementStore repository is not a side project — it is the Accounts Payable backbone of the RestoBooks platform. Here is a precise mapping of what exists and its strategic value:

| Capability | Status | Notes |
| --- | --- | --- |
| AI Invoice Data Extraction (OCR/Parsing) | ✅ DONE | The hardest AP automation piece. Most competitors charge $300/mo for this alone. |
| Invoice Generation (PDF/Structured) | ✅ DONE | Vendor invoice workflow complete. Feeds COGS categorization. |
| Invoice Store + Retrieval (Database) | ✅ DONE | Persistent AP ledger. Foundation for food cost trending. |
| REST API with CRUD (Lambda) | ✅ DONE | Serverless-native. Scales to zero. Matches your AWS stack. |
| Bank Feed Integration (Plaid) | 🔨 NEXT | Week 1 priority. Unlocks bank-side transaction data. |
| AI Categorization Agent (Claude) | 🔨 NEXT | Week 2. Sits on top of your existing invoice + bank data. |
| Toast POS Integration | 🎯 WEEK 3-4 | Enriches bank data. Apply for Toast partner sandbox Day 1. |
| Settlement Reconciliation Agent | 🎯 WEEK 3-4 | Crown jewel demo. Bank vs Toast vs Invoice triangulation. |
| Dashboard / Analytics UI | 🎯 WEEK 4 | Minimal React dashboard. Anomaly cards + category breakdown. |

| KEY INSIGHT | Your AI invoice extraction is xtraCHEF's core feature — the one Toast acquired a company for in 2021. You have already built the hardest part of their $300/location/month product. |
| --- | --- |

# 2. Architecture: How It All Connects

Your existing Lambda API sits at the center of a 3-source data model. The strategic insight is that no competitor triangulates all three simultaneously:

| Layer | Components | Your App's Role |
| --- | --- | --- |
| Source 1 Invoices | Your InvoiceManagementStore Lambda OCR extraction → structured line items Sysco, US Foods, Gordon Food Service | Already built. Feeds COGS. Detects food cost variance vs theoretical. |
| Source 2 Bank Feed | Plaid API (sandbox, free) All cash in/out Vendor ACH, rent, utilities, payroll | Week 1 build. The universal input — works with ANY POS or no POS. |
| Source 3 Toast POS | Toast REST API (OAuth 2.0) Orders, Payments, Employees Real-time webhooks | Week 3 enrichment. Explains bank settlement amounts. Not required to launch. |
| Agent Layer | Categorization Agent (Claude Sonnet) Reconciliation Agent (nightly) Anomal Detection Agent (event-driven) | Sits above all 3 sources. Reasons across them. No competitor does this. |
| Merchant Memory | DynamoDB lookup table 'SYSCO FOODS 847291' → Food Cost Learns from human corrections | Eliminates repeat LLM calls. Gets faster and cheaper over time. |

| ARCHITECTURAL MOAT | Your Invoice Lambda + Plaid bank feed + Toast POS creates a triangulated view of restaurant finances that neither Toast IQ, xtraCHEF, nor QuickBooks sees. Each only sees one side. You see all three. |
| --- | --- |

# 3. The 4-Week Sprint Plan

Your existing app completes the pre-work. The remaining 4 weeks are entirely focused on the agent layer and integration.

| Sprint | Build Tasks | End-of-Week Deliverable |
| --- | --- | --- |
| Week 1 Bank Feed | - Wire Plaid sandbox → new IngestLambda - Normalize Plaid transactions to unified schema - Connect IngestLambda to EventBridge (txn.ingested event) - Extend DynamoDB: add transactions + merchant_memory tables - Link existing invoice store to DynamoDB (shared infra) - Apply for Toast partner sandbox access (Day 1 — takes time) | ✓ Bank transactions flowing into DynamoDB Your invoice Lambda already handles the DB layer — reuse the pattern |
| Week 2 Categorization Agent | - Build CategorizationLambda (triggered by txn.ingested) - Claude Sonnet API call with restaurant CoA in system prompt - Inject invoice data as context (Sysco invoices → food cost mapping) - Merchant memory read/write (skip LLM if merchant known) - Confidence scoring + NEEDS_REVIEW flagging - Basic React UI: transaction list with category + confidence badge | ✓ Transactions auto-categorized with invoice context Your OCR output directly feeds the agent's context window |
| Week 3 Reconciliation Agent + Toast | - ReconciliationLambda: nightly schedule + on-demand trigger - Food cost % check: invoice COGS vs Toast sales data - Duplicate charge detection across bank + invoice sources - Toast sandbox: pull Orders + Payments + Employees APIs - Settlement matching: bank deposit vs Toast batch - Plain-English anomaly summaries via Claude | ✓ Bank vs Invoice vs Toast triangulation live "Your food cost this week was 41% — 6pts above target. Sysco charged twice." |
| Week 4 Demo Polish | - Delivery profitability agent (DoorDash fees from Toast vs bank) - Conversational query: 'What did I spend on food this month?' - Onboarding flow: connect bank → restaurant type → done - Seed realistic demo data (full month, fictional restaurant) - Anomaly card UI: flagged items with one-click resolution - Record demo video. Prep investor/customer pitch. | ✓ Showable, investable POC The 'wow moment': agent catches a duplicate Sysco charge before the owner does |

# 4. The Unique Advantage Your Invoice App Gives You

This is what separates RestoBooks from every competitor starting from scratch:

| Advantage | Without Invoice App | With Your Invoice App |
| --- | --- | --- |
| Food Cost Accuracy | Estimate from bank charges only (~±15% error) | Line-item COGS from OCR invoices (±2% accuracy) |
| Vendor Invoice Reconciliation | Manual. Accountant reviews paper invoices. | Agent matches bank ACH to extracted invoice automatically |
| Price Spike Detection | Not possible without line-item data | 'Beef tenderloin up 18% vs last order from Sysco' |
| AP Automation | Not available. Must build from scratch. | Already live. Core xtraCHEF feature replicated. |
| Demo Credibility | Bank feed only — looks like Mint for restaurants | Full AP + bank + POS — looks like a complete product |

# 5. Competitive Position After POC

| Capability | RestoBooks | xtraCHEF | Toast IQ | QuickBooks |
| --- | --- | --- | --- | --- |
| AI Invoice Extraction (OCR) | ✅ | ✅ | ❌ | ❌ |
| Bank Feed Reconciliation | ✅ | ⚠️ Weak | ❌ | ⚠️ Manual |
| AI Transaction Categorization | ✅ | ❌ Rule-based | ❌ | ❌ |
| Toast POS Integration | ✅ | ✅ | ✅ Native | ⚠️ Via bridge |
| Delivery Profitability Agent | ✅ | ❌ | ❌ | ❌ |
| Cross-source Anomaly Detection | ✅ | ❌ | ❌ | ❌ |
| POS-Agnostic (Square/Clover) | ✅ | ❌ Toast only | ❌ Toast only | ✅ |
| Conversational CFO Queries | ✅ | ❌ | ⚠️ Ops only | ❌ |

# 6. Day 1 Actions

Start these in parallel on Day 1 — they have long lead times:

| # | Action | Effort | Why Now |
| --- | --- | --- | --- |
| 1 | Apply for Toast Integration Partner sandbox access at dev.toasttab.com | 30 min | Approval takes weeks |
| 2 | Sign up for Plaid developer account (sandbox is free, instant access) | 15 min | Needed for Week 1 |
| 3 | Create new DynamoDB tables: transactions, merchant_memory, recon_sessions | 2 hrs | Foundation for all agents |
| 4 | Add Claude API key to your Lambda environment secrets | 15 min | Needed for Week 2 agent |
| 5 | Create a fictional demo restaurant with 30 days of realistic transactions | 3 hrs | Powers your demo on Day 28 |
| 6 | Define your restaurant Chart of Accounts JSON (use the CoA from our plan) | 1 hr | Agent system prompt core |

| THE PITCH AFTER 4 WEEKS | "We built the agentic CFO for restaurants. Connect your bank in 2 minutes. Every transaction is categorized using your actual vendor invoices — not generic rules. We catch the Sysco double-charge, the DoorDash fee that ate your margin, the payroll that hit twice. QuickBooks gives you a spreadsheet. We give you answers." |
| --- | --- |

— End of Strategic Plan —

InvoiceManagementStore → RestoBooks | March 2026